## ACTIONS
Action Log
Joint Audit and Risk Committee Public Police & Crime Meetings
Action Number | Meeting Date | Agenda Item | Action Required | Action Owner | Target completion Date | Action Progress (Short Description) | Action Status
1 | 2025-09-24 | 3 | To add a closed session for the Committee to discuss the Cyber Security Audit in more detail. | LD/KG | 2026-03-01 | Will be arranged when report has been finalised.Closed Session Meeting arranged for 17 March - JB presenting | Complete
2 | 2025-09-24 | 6 | For additional information to be added to the risk report to indicate the when, where and why a risk has been escalated, along with the timeframes. | DW | 2026-03-01 | DW has confirmed that this can be discussed in a closed session with the Committee due to the level of detail and sensitivity of items. This will be arranged for the end of the meeting in March 2026. Closed session arranged for the 17 March with JB to present. | Complete
3 | 2025-11-25 | 4.iii | For RSM to report back to JARC at either March or June 2026 meeting, confirming whether or not they are satisfied the custody-related data now adequately reconciles between various reports. | RSM | 2026-06-01 | RSM have confirmed that this action will be brought to the June meeting. | Ongoing

## Archived Actions
Archived Actions
Joint Audit and Risk Committee Public Police & Crime Meetings
Action Number | Meeting Date | Subject Matter | Action Required | Action Owner | Target completion Date | Action Progress (Short Description) | Action Status
3 | 2023-05-25 | 5 (iii) | The draft Statutory Accounts for 2022/23 are to be published by the 31 May 2023 | Jean Cass | 2023-05-31 | The draft of the Statutory accounts were published on the SCO website on the 31 May 2023 and are avaialble for members on Huddle | Complete
4 | 2023-05-25 | 7 | DW and VF to discuss the use of the Force’s current governance chart for the SCO and Force’s AGS 2022/23. | Deb Wilne & Victoria Farrar | 2023-07-26 |  | Complete
1 | 2023-07-26 | 1 | JC to add on Huddle the Staffordshire Police Strategy. | Jean Cass | 2023-08-02 | Added to Huddle | Complete
2 | 2023-07-26 | 8 | JC to add to Huddle a copy of Lee Rowley’s report | Jean Cass | 2023-08-02 | Added to Huddle | Complete
1 | 2023-05-25 | 3 | DW to consider adding a note of the PSED to the Force’s final version of the Annual Governance Statement (AGS). | Deb Wilne | 2023-07-26 | DW advised that considerations will be picked up with the AGS | Complete
2 | 2023-05-25 | 5 (ii) | EY Auditors to provide ETAP members with update on the VFM statement | EY | 2023-07-26 | Update given at the meeting on the 22 Nov | Complete
5 | 2023-05-25 | 8 | DW to consider matters raised at the public ETAP meeting for the Force’s AGS | Deb Wilne | 2023-07-26 | DW shared feedback at the meeting 22 Nov | Complete
1 | 2023-09-27 | 2 | DW to share with members of a copy of the Force's final AGS for 2022/23 | Deb Wilne | 2023-11-22 | DW shared feedback at the meeting 22 Nov and a copy of the Force's final AGS | Complete
2 | 2023-09-27 | 4 | VJ to provide CISP background information including a copy of the original business case to DW | Victoria Jones | 2023-11-22 | Background information provided | Complete
1 | 2023-11-22 | 4 (ii) | JR to give an update on the Force’s Ethic’s Panel | Force's Professional Standards Department | when available | An officer from the Force’s Professional Standards Department (PSD) will give an update to a future meeting of ETAP’s Ethics and Review Panel | Complete
1 | 2024-05-31 | 4 | JC to arrange for members briefings in Cybercrime and on the Force’s Digital and Data strategy. | JC | 2024-12-04 | The specific date is to be confirmed as the force is currently appointing a new Director of IT & DDAT who should be in post by the end of 2024. It is recommended therefore that this briefing will be scheduled for qtr. 1 of 2025/26. The force will look to ensure that the cybercrime element is also covered at this time. | Complete
2 | 2024-05-31 | 7 | ETAP members requested a briefing on the financial health and sustainability position of the Force for a future ETAP meeting. | JBl | 2024-09-25 | Covered by the Going Concern Assessment 2023.24 Agenda item 4 (ii) | Complete
3 | 2024-05-31 | 8 | LC to share a brief verbal update on the work of SCO at future ETAP public meetings. | LC | 2024-12-04 | Full agenda for September meeting - Briefing to be arranged at a later date. Moved to meeting 26/02/2025 | Complete
1 | 2024-09-25 | 7 - Key HMICFRS reports. Section 4 Force Management Statement 6 | Arrange a meeting with JK and DW to review update on AFI's | KG | 2024-12-04 | KG to liaise and arrange a meeting with JK & DW. JK to arrange directly with DW a meeting time, contact details shared. JK attending the Inspection and Audit Board on 20.11.24 and will provide an update at meeting on 4.12.2024 | Complete
1 | 2024-12-04 | 2. Apologies,minutes,actions | ETAP to consider a member attending the governance meeting occasionally | CK | 26.02.2025 | ETAP to discuss occasionally attending Inspection and Audit Board Meetings and who will attend. **This will be considered as part of the Joint Audit and Risk Committee ** | Complete
1 | 2025-02-26 | 6. External Audit | Force to compile one tracking document for all risks and actions being taken which can be brought to each ETAP meeting | DW | 10.06.2025 | DW confirmed the force will continue to track all inspection and audit recommendations through it's action planning systems and report to ETAP twice yearly as per the reporting schedule. Items from External Audit are captured as part of the process. | Complete
1 | 10.06.2025 | 4.i. Draft Annual Report 2024/25 | To ensure the Force AGS adequately reflects the issues raised by RSM and JB. Vetting and Custody in the AGS | DW & JB | 24.09.2025 | AGS is due to be presented at the September meeting. | Complete
1 | 10.06.2025 | 4.i. Draft Annual Report 2024/25 | RSM's report to be amended to reflect operational lead accountabilities in Appendix A | RSM | 24.09.2025 | Updated Annual Report received with amendments to Appendix A - lead accountabilities. | Complete
2 | 2025-09-24 | 5 | JB to review the request for the organisation making the Gifts & Hospitality Offer to be shown in the report, and to feed back on this to the Committee | JB | 2025-11-01 | G&H Report will be produced by ACU for next year and will include the additional information as requested by the Committee | Complete
4 | 2025-09-24 | 4 | LC to review the reporting for Gifts & Hospitality regarding estimating the value for offers made | LC | 2025-11-01 | This will be implemented in the SCO and the Gifts & Hospitality Report for 25.26 will include this detail. | Complete

## Do not Delete (hidden)
Complete
Ongoing
Superseded