## Action Log
Action Plan
Ethics, Transparency and Audit Panel Public Fire & Rescue Meetings
Action Number | Meeting Date | Agenda Item | Action Required | Action Owner | Target completion Date | Action Progress (Short Description) | Action Status | Action Status
1 | 16.06.2025 | 4.i | Committee would like to see the Workforce Strategy Document | KG & DG | 2025-09-24 | DG has shared the Work Force Planning Board Terms of Reference which has been shared with Committee members on Huddle. | Complete
2 | 16.06.2025 | 4.ii | Value for Money report added as a standard agenda item for the 3rd quarter meeting annually | KG | 2025-09-24 | This has been done on the JARC Annual Plan | Complete
3 | 16.06.2025 | 8. AOB | Committee have asked if payslips can be issued via email rather than in the post. | KG | 2025-09-24 | Finance have confirmed this can be done, shared email addresses and this will be in place from September meeting. | Complete

## Archived Actions
Archived Actions
Ethics, Transparency and Audit Panel Public Fire & Rescue Meetings
Action Number | Meeting Date | Subject Matter | Action Required | Action Owner | Target completion Date | Action Progress (Short Description) | Action Status
1 | 2023-02-22 | 2 (iii) | FARS Inspection review process - SW & BT to meet with Will Parkinson and Nick Jones at FARS | SW & BT | 2023-05-24 | Meeting arranged for 3 March with SW & BT & WP at FARS | Complete
2 | 2023-02-22 | 2 (iii) | To supply a copy of the flow chart of HMICFRS Inspection recommendations | RB | 2023-05-24 | RB to send a screen shot of the action tracker to members | Complete
3 | 2023-02-22 | 7 AOB | To provide an update on the Internal Audit Benchmarking group report at a future meeting of the Finance Panel meeting | DG | tbc | Agreed to carry this forward to a future meeting of the Finance Panel. | Complete
1 | 2023-11-23 | 1 | A request to report back at the next ETAP public meeting with the results of the on-call consultation work | RB | 2024-02-27 | Update given at the meeting on the 27 Feb | Complete
1 | 2024-02-27 | 6 | RB to feedback to the Panel on the results of the Hives Survey. | RB | 30/05/204 19/06/2024 | Update given at the meeting on the 19 June 2024 | Complete
1 | 2024-09-27 | 5.(i) Gifts & Hospitality Report | CBr to add a review of the Fire’s Gifts and Hospitality Register when updated | CBr | 2025-03-01 | CBr has updated the policy, some minor changes made and policy is out to a 12 week consultation before being finalised and will come back to the Finance Panel Insight meeting in March 2025 | Complete
1 | 2024-12-05 | 4. CFO Update | RB to update ETAP with ongoing situation with a new College of Fire | RB | 2025-02-01 | On the agenda for meet 25.2.25 | Complete
2 | 2024-12-05 | 4. CFO Update | Update ETAP with progress in managing Grenfell Phase 2 Recommendations | RB | 2025-02-01 | On the agenda for meet 25.2.25 | Complete
5 | 2024-12-05 | 7. (iii) IT and Cyber Security Report | DG to provide an update on the progress of the audit actions at the Finance Panel Meeting on 31 January 2025. | DG | 2025-02-01 | Head of ICT to be invited to FP Insight Meeting in March to provide update on the progress of Cyber Security Report - therefore this action is superseded. | Superseded
6 | 2024-12-05 | 7. (iii) IT and Cyber Security Report | Invite the Head of IT to the Finance Panel meeting January 2025 to discuss the report. | KG | 2025-03-01 | Confirmed that Head of IT will attend the Insight Meeting in March. Added to the Agenda | Complete
3 | 2024-12-05 | 4. CFO Update | CB to consider adding review of Falls Response and Home from Hospital initiatives to the ERP workplan. | CB | 2025-02-01 | Discussed at meeting and requestd a member of FARS to attend the next ERP meeting in May to discuss this rather than an ERP review. | Complete
4 | 2024-12-05 | 5. Deputy Chair Update | CB to score Falls Response and Home from Home initiatives using the Matrix and report back at the next ETAP meeting. | CB | 2025-02-01 | Discussed at meeting and requestd a member of FARS to attend the next ERP meeting in May to discuss this rather than an ERP review. | Complete
1 | 2025-02-25 | 4. Internal Audit Draft Annual Strategy | LD to update the table on page 10 and 11 of the report with colour coding and definitions | LD | 2025-06-16 | Updated report received from LD with amends. | Complete
2 | 2025-02-25 | 4. Internal Audit Draft Annual Strategy | RSM to clarify to ETAP the progress towards greater consolidation of work plans between organisations to ensure RSM is seeking value for money from the internal audit work plan. | LD & DH | 2025-06-16 | LD from RSM has confirmed that where possible reviews will be consolidated. Acknowledging that this will not always be possible given the specific scope of some reviews. | Complete
3 | 2025-02-25 | 4. Internal Audit Draft Annual Strategy | RSM to clarify as to which party is due to sign off the Charter. | LD & DH | 2025-06-16 | RSM confirmed that the approval of the charter is the responsibility of ETAP. | Complete
4 | 2025-02-25 | 6. Fire Governance Report | ETAP to set aside time to consider actions arising from the Grenfell Phase 2 at a future session | CK | 2025-06-16 | Member of FARS attended ERP meeting 20 May 2025 to discuss the report and FARS response. | Complete
5 | 2025-02-25 | 7. Precept reports | At least 1 ETAP member to attend a "financial Challenge" session at a future agreed date | CK & KG | 2025-06-16 | JK attended session 28.3.25 on Teams. | Complete

## Do not Delete (hidden)
Complete
Ongoing
Superseded