## Action Log
Action Plan
Ethics, Transparency and Audit Panel Public Fire & Rescue Meetings
Action Number | Meeting Date | Agenda Item | Action Required | Action Owner | Target completion Date | Action Progress (Short Description) | Action Status | Action Status
1 | 2025-09-25 | 1 | For JARC to review that the AI policy in relation to Cyber Security has been implemented. | DG/CK | 2026-03-19 | AI Policy shared with JARC on Huddle for review 15.1.26 | Complete
1 | 2025-11-25 | 3.ii | DG/Risk Team to check the broad risks set out in RSM's Risk Benchmarking Report align appropriately with FARS 'Risk Register'. | DG/VA | 2026-03-19 | VA has shared an update confirming that this is complete. This has been shared with JARC members but not in the Punlic domain due to specific references to the strategic risk register. | Complete
2 | 2025-11-25 | 3.iii | FARS Risk team to please review and consider the visual risk reporting format as shown in the RSM report as a possible format to clarify risk reporting for FARS. | VA | 2026-03-19 | The Committee requested that future risk reporting be presented in the specific register format referenced on page 5. As our current reporting is generated directly from the risk software tool,JCAD, it is challenging to replicate this format exactly however, I have provided a similar layout to demonstrate how the information can be presented using our existing system. We are continuing to review reporting options and can confirm that we are planning to transition to RSM’s reporting approach from October, which will support a more consistent and aligned format going forward. | Complete
3 | 2025-11-25 | 3.iv | For CBr to review the Counter Fraud and Corruption Policy | CBr | 2026-03-19 | This will be reviewed prior to the JARC Meeting on 2 July 2026 | Ongoing
4 | 2025-11-25 | 4 | For DG to confirm whether the process to support high potential staff and potential leaders is in place | DG | 2026-03-19 | Copy of the Talent Progression Programme shared with JARC on Huddle 15.1.26 | Complete

## Archived Actions
Archived Actions
Ethics, Transparency and Audit Panel Public Fire & Rescue Meetings
Action Number | Meeting Date | Subject Matter | Action Required | Action Owner | Target completion Date | Action Progress (Short Description) | Action Status
1 | 2023-02-22 | 2 (iii) | FARS Inspection review process - SW & BT to meet with Will Parkinson and Nick Jones at FARS | SW & BT | 2023-05-24 | Meeting arranged for 3 March with SW & BT & WP at FARS | Complete
2 | 2023-02-22 | 2 (iii) | To supply a copy of the flow chart of HMICFRS Inspection recommendations | RB | 2023-05-24 | RB to send a screen shot of the action tracker to members | Complete
3 | 2023-02-22 | 7 AOB | To provide an update on the Internal Audit Benchmarking group report at a future meeting of the Finance Panel meeting | DG | tbc | Agreed to carry this forward to a future meeting of the Finance Panel. | Complete
1 | 2023-11-23 | 1 | A request to report back at the next ETAP public meeting with the results of the on-call consultation work | RB | 2024-02-27 | Update given at the meeting on the 27 Feb | Complete
1 | 2024-02-27 | 6 | RB to feedback to the Panel on the results of the Hives Survey. | RB | 30/05/204 19/06/2024 | Update given at the meeting on the 19 June 2024 | Complete
1 | 2024-09-27 | 5.(i) Gifts & Hospitality Report | CBr to add a review of the Fire’s Gifts and Hospitality Register when updated | CBr | 2025-03-01 | CBr has updated the policy, some minor changes made and policy is out to a 12 week consultation before being finalised and will come back to the Finance Panel Insight meeting in March 2025 | Complete
1 | 2024-12-05 | 4. CFO Update | RB to update ETAP with ongoing situation with a new College of Fire | RB | 2025-02-01 | On the agenda for meet 25.2.25 | Complete
2 | 2024-12-05 | 4. CFO Update | Update ETAP with progress in managing Grenfell Phase 2 Recommendations | RB | 2025-02-01 | On the agenda for meet 25.2.25 | Complete
5 | 2024-12-05 | 7. (iii) IT and Cyber Security Report | DG to provide an update on the progress of the audit actions at the Finance Panel Meeting on 31 January 2025. | DG | 2025-02-01 | Head of ICT to be invited to FP Insight Meeting in March to provide update on the progress of Cyber Security Report - therefore this action is superseded. | Superseded
6 | 2024-12-05 | 7. (iii) IT and Cyber Security Report | Invite the Head of IT to the Finance Panel meeting January 2025 to discuss the report. | KG | 2025-03-01 | Confirmed that Head of IT will attend the Insight Meeting in March. Added to the Agenda | Complete
3 | 2024-12-05 | 4. CFO Update | CB to consider adding review of Falls Response and Home from Hospital initiatives to the ERP workplan. | CB | 2025-02-01 | Discussed at meeting and requestd a member of FARS to attend the next ERP meeting in May to discuss this rather than an ERP review. | Complete
4 | 2024-12-05 | 5. Deputy Chair Update | CB to score Falls Response and Home from Home initiatives using the Matrix and report back at the next ETAP meeting. | CB | 2025-02-01 | Discussed at meeting and requestd a member of FARS to attend the next ERP meeting in May to discuss this rather than an ERP review. | Complete
1 | 2025-02-25 | 4. Internal Audit Draft Annual Strategy | LD to update the table on page 10 and 11 of the report with colour coding and definitions | LD | 2025-06-16 | Updated report received from LD with amends. | Complete
2 | 2025-02-25 | 4. Internal Audit Draft Annual Strategy | RSM to clarify to ETAP the progress towards greater consolidation of work plans between organisations to ensure RSM is seeking value for money from the internal audit work plan. | LD & DH | 2025-06-16 | LD from RSM has confirmed that where possible reviews will be consolidated. Acknowledging that this will not always be possible given the specific scope of some reviews. | Complete
3 | 2025-02-25 | 4. Internal Audit Draft Annual Strategy | RSM to clarify as to which party is due to sign off the Charter. | LD & DH | 2025-06-16 | RSM confirmed that the approval of the charter is the responsibility of ETAP. | Complete
4 | 2025-02-25 | 6. Fire Governance Report | ETAP to set aside time to consider actions arising from the Grenfell Phase 2 at a future session | CK | 2025-06-16 | Member of FARS attended ERP meeting 20 May 2025 to discuss the report and FARS response. | Complete
5 | 2025-02-25 | 7. Precept reports | At least 1 ETAP member to attend a "financial Challenge" session at a future agreed date | CK & KG | 2025-06-16 | JK attended session 28.3.25 on Teams. | Complete
1 | 16.06.2025 | 4.i | Committee would like to see the Workforce Strategy Document | KG & DG | 2025-09-24 | DG has shared the Work Force Planning Board Terms of Reference which has been shared with Committee members on Huddle. | Complete
2 | 16.06.2025 | 4.ii | Value for Money report added as a standard agenda item for the 3rd quarter meeting annually | KG | 2025-09-24 | This has been done on the JARC Annual Plan | Complete
3 | 16.06.2025 | 8. AOB | Committee have asked if payslips can be issued via email rather than in the post. | KG | 2025-09-24 | Finance have confirmed this can be done, shared email addresses and this will be in place from September meeting. | Complete

## Do not Delete (hidden)
Complete
Ongoing
Superseded