## Action Log
Action Plan
Ethics, Transparency and Audit Panel Public Fire & Rescue Meetings
Action Number | Meeting Date | Agenda Item | Action Required | Action Owner | Target completion Date | Action Progress (Short Description) | Action Status | Action Status
1 | 2024-09-27 | 5.(i) Gifts & Hospitality Report | CBr to add a review of the Fire’s Gifts and Hospitality Register when updated | CBr | 2025-03-01 | CBr has updated the policy, some minor changes made and policy is out to a 12 week consultation before being finalised and will come back to the Finance Panel Insight meeting in March 2025 | Complete
1 | 2024-12-05 | 4. CFO Update | RB to update ETAP with ongoing situation with a new College of Fire | RB | 2025-02-01 | On the agenda for meet 25.2.25 | Complete
2 | 2024-12-05 | 4. CFO Update | Update ETAP with progress in managing Grenfell Phase 2 Recommendations | RB | 2025-02-01 | On the agenda for meet 25.2.25 | Complete
3 | 2024-12-05 | 4. CFO Update | CB to consider adding review of Falls Response and Home from Hospital initiatives to the ERP workplan. | CB | 2025-02-01 | Awaiting Update | Ongoing
4 | 2024-12-05 | 5. Deputy Chair Update | CB to score Falls Response and Home from Home initiatives using the Matrix and report back at the next ETAP meeting. | CB | 2025-02-01 | Awaiting Update | Ongoing
5 | 2024-12-05 | 7. (iii) IT and Cyber Security Report | DG to provide an update on the progress of the audit actions at the Finance Panel Meeting on 31 January 2025. | DG | 2025-02-01 | Head of ICT to be invited to FP Insight Meeting in March to provide update on the progress of Cyber Security Report - therefore this action is superseded. | Superseded
6 | 2024-12-05 | 7. (iii) IT and Cyber Security Report | Invite the Head of IT to the Finance Panel meeting January 2025 to discuss the report. | KG | 2025-03-01 | Confirmed that Head of IT will attend the Insight Meeting in March. Added to the Agenda | Complete

## Archived Actions
Archived Actions
Ethics, Transparency and Audit Panel Public Fire & Rescue Meetings
Action Number | Meeting Date | Subject Matter | Action Required | Action Owner | Target completion Date | Action Progress (Short Description) | Action Status
1 | 2023-02-22 | 2 (iii) | FARS Inspection review process - SW & BT to meet with Will Parkinson and Nick Jones at FARS | SW & BT | 2023-05-24 | Meeting arranged for 3 March with SW & BT & WP at FARS | Complete
2 | 2023-02-22 | 2 (iii) | To supply a copy of the flow chart of HMICFRS Inspection recommendations | RB | 2023-05-24 | RB to send a screen shot of the action tracker to members | Complete
3 | 2023-02-22 | 7 AOB | To provide an update on the Internal Audit Benchmarking group report at a future meeting of the Finance Panel meeting | DG | tbc | Agreed to carry this forward to a future meeting of the Finance Panel. | Complete
1 | 2023-11-23 | 1 | A request to report back at the next ETAP public meeting with the results of the on-call consultation work | RB | 2024-02-27 | Update given at the meeting on the 27 Feb | Complete
1 | 2024-02-27 | 6 | RB to feedback to the Panel on the results of the Hives Survey. | RB | 30/05/204 19/06/2024 | Update given at the meeting on the 19 June 2024 | Complete

## Do not Delete (hidden)
Complete
Ongoing
Superseded