## Action Log
Action Plan
Ethics, Transparency and Audit Panel Public Fire & Rescue Meetings
Action Number | Meeting Date | Agenda Item | Action Required | Action Owner | Target completion Date | Action Progress (Short Description) | Action Status | Action Status
1 | 2022-10-31 | 6 | Implementation of New Accounts package - BS asked for further updates at the Finance Panel. | JC | 2022-11-16 | Finance Panel November meeting cancelled - updates given at the Finance Panel meeting on the 30th January | Complete | Complete

## Archived Actions
Archived Actions
Ethics, Transparency and Audit Panel Public Fire & Rescue Meetings
Action Number | Meeting Date | Subject Matter | Action Required | Action Owner | Target completion Date | Action Progress (Short Description) | Action Status
1 | 2022-02-16 | 2 (ii) | To check for links to ETAP reviews on the FARS website | Corrina Bradley | 2022-05-25 | CB confirmed that links are in place | Complete | Complete
2 | 2022-05-25 | 3 (i) | To have a discussion on future timetabling of Fire meetings | JC | 2022-07-25 | This proposal is being discovered at Chair Catch Up meetings in June and July 2022. | Complete | Ongoing
3 | 2022-05-25 | 3 (ii) | To reply with comments on the Gifts, Hospitality and Expenses Report | CBR | 2022-07-25 | A response from CBR has been received and forward to JK on the 8 June 2022 | Complete | Superseded
4 | 2022-05-25 | 4 | To invite the chair of PFCP to attend a future ETAP meeting | JC | 2022-07-25 | Email sent on the 17 June inviting the chair to a future meeting | Complete
5 | 2022-05-25 | 6 (i) | To share a link to the National Audit Office (NAO) website for assessments | JC | 2022-07-25 | Link shared with the Chair of ETAP | Complete
1 | 2022-05-25 | 1 (ii) | To prepare a summary report of the Chair's Annual Report for the SCO website | BS & JK | 2022-07-25 | Prepared by JK, on SCO website | Complete
1 | 2022-07-27 | 2 (ii) | CBR to supply a report the Expenses, Gifts and Expenses, for the period ending 31 March 2022 to the next ETAP meeting on the 31 October | CBR | 2022-10-31 | On today's agenda item 4 | Complete

## Do not Delete (hidden)
Complete
Ongoing
Superseded